* 2.27 - Meeting Record

Objectives:

Decide topic: Urbanization in Africa

Decide to use webflow as our landing page

Every Thursday 8 p.m. (Canberra time) meeting

Individual work (Due by next Meeting):

Xi Chen: Working on Landing Page

Yifei Tao: set up urls and server side

Qixuan Ren & Yuexin Chen: Readme file on gitlab

* 3.2 – Meeting Record

Welcome our new team member


Individual work (Due by next Meeting):

Xi Chen & Fei Wu: Working on Team charter

Yifei Tao & Qixuan Ren & Yuexin Chen: Working on Project Overview Doc

* 3.4 – Meeting Record

Change the topic: Agriculture in Africa (decided by vote)



Think about key modules: natural calamities, plague of locusts, crop yield...

Discuss the flow path of this project

Modify the landing page

Individual work: (Due by next meeting)

Xi Chen & Fei Wu: team charter

Xi Chen: design document cover

Yifei Tao & Qixuan Ren & Yuexin Chen: do the part 1, part 2, part 3, respectively (Project Overview Doc)

* 3.11 – Meeting Record

imagine and plan the final results (dashboard)

Analyse challenges and issue

Individual work: (Due by next meeting)

Xi Chen & Qixuan Ren: research the problems African agriculture faces and the causes.

Fei Wu & Yifei Tao & Yuexin Chen: research on tools and data of DE Africa (find which tool applies to this project? How to solve problem by tools?)

Note: focus climate, write info to skeleton.doc

* 3.19 – Meeting Record

Define the point of view of our project, and select a specific country(South Africa) to narrow the scope of the study.

Discuss the problem, solution and challenge.

Individual work:

Task 1(due by 3/22):

Stakeholder analysis：Qixuan

Ecosystem mapping: Xi & Yifei

Mapping relationship stakeholder with issues: Fei & Yuexin

Task2 (due by next meeting):

Agriculture status in South Africa: Xi & Fei

POV: qixuan & yuexin & yifei